## Slide 1: CET311
Diagramming Questions
Dr R L Warrender
Project Management

## Slide 2: Exercise 1
Tasks Precedence Time
a - 6 weeks
b - 4 weeks
c - 3 weeks
d a 4 weeks
e b 3 weeks
f b 2 weeks
g c 3 weeks
h d,e 2 weeks
i f 1 week
j g,i 2 weeks

## Slide 3: Exercise 2
Tasks Precedence Time
a - 3 weeks
b - 5 weeks
c a 7 weeks
d b 5 weeks
e c, d 6 weeks
f b 4 weeks
g b 8 weeks
h c, d 4 weeks
i e, f 3 weeks

## Slide 4: Exercise 3
Tasks Precedence Time
a - 2 weeks
b - 4 weeks
c - 3 weeks
d a 3 weeks
e a 5 weeks
f c 6 weeks
g c 4 weeks
h d 4 weeks
i d 8 week
j b, e, f, i 2 weeks
k - 4 weeks
l g, k 3 weeks

## Slide 5: Exercise 4
Tasks Precedence Time
a - 3 weeks
b a 5 weeks
c a 3 weeks
d c 1 weeks
e b 3 weeks
f b, d 4 weeks
g c 2 weeks
h g, f 3 weeks
i e, h 1 weeks

## Slide 6: Exercise 5
Tasks Precedence Time
a - 3 weeks
b - 5 weeks
c a 14 weeks
d a 5 weeks
e b 4 weeks
f b 7 weeks
g d, e 8 weeks
h g, f 5 weeks

## Slide 7: Exercise 6
Tasks Precedence
a -
b -
c a
d a
e -
f c
g c
h d
i a, b
j g, h
k i
l e, i
m j, k
n m, l
o f, n

## Slide 8: Exercise 7
Tasks Precedence Time
a - 3 weeks
b a 5 weeks
c a 3 weeks
d c 1 weeks
e b 3 weeks
f b, d 4 weeks
g c 2 weeks
h g, f 3 weeks
i e, h 1 week

## Slide 9: Exercise 8
Tasks Precedence Time
a - 2 days
b - 1 days
c a 4 days
d a, b 3 days
e - 4 days
f c 1 days
g d, e 3 days
h g, f 1 days
i g 2 days

## Slide 10: Exercise 9
Tasks Precedence Time
a - 3 days
b - 4 days
c a 2 days
d b 5 days
e b 2 days
f b, c 4 days
g d 3 days
h e 6 days
i g 3 days
j f, i 4 days
k g 5 days
l d, h 4 days

## Slide 11: Exercise 10
Tasks Precedence Time
a - 2 weeks
b - 4 weeks
c - 3 weeks
d a 3 weeks
e a 5 weeks
f c 6 weeks
g c 4 weeks
h d 1 weeks
i d 8 weeks
j b, e, f, i 2 weeks
K - 4 weeks
l g, k 3 weeks